## Sheet1
Date | Activity | Date | Activity | Text Placement
2017-01-21 | Meeting with GoldSand | 2017-01-21 | Meeting with GoldSand | 10
2017-01-26 | Develop Release 1.0 | 2017-01-26 | Develop Release 1.0 | -10
2017-01-27 | Add code and test | 2017-01-27 | Add code and test | 10
2017-02-07 | Finish Release 1.0 | 2017-02-07 | Finish Release 1.0 | -10
2017-02-09 | Meeting with GoldSand | 2017-02-09 | Meeting with GoldSand | 10
2017-02-10 | Develop Release 2.0 | 2017-02-10 | Develop Release 2.0 | -10
2017-02-24 | Finish Release 2.0 | 2017-02-24 | Finish Release 2.0 | 10
2017-02-25 | Meeting with GoldSand | 2017-02-25 | Meeting with GoldSand | -10
2017-02-26 | Making API Guide | 2017-02-26 | Making API Guide | 10
2017-03-05 | Finish API Guide | 2017-03-05 | Finish API Guide | -10
2017-03-06 | Deliver Solution | 2017-03-06 | Deliver Solution | 10
Formulas:
Date = IF([Date]<>"", [Date], "")