## Sheet1
Date | Activity | Date | Activity | Text Placement
2017-01-21 | Meeting with GoldSand | 2017-01-21 | Meeting with GoldSand | 10
2017-01-26 | Develop Beta 0.9 | 2017-01-26 | Develop Beta 0.9 | -10
2017-01-27 | Add code and test | 2017-01-27 | Add code and test | 10
2017-02-07 | Finish Beta 0.9 | 2017-02-07 | Finish Beta 0.9 | -10
2017-02-09 | Meeting with GoldSand Collect new requirements | 2017-02-09 | Meeting with GoldSand Collect new requirements | 10
2017-02-10 | Develop Beta 0.9.1 | 2017-02-10 | Develop Beta 0.9.1 | -10
2017-02-18 | Meeting with GoldSand Collect new requirements | 2017-02-18 | Meeting with GoldSand Collect new requirements | 10
2017-02-19 | Continue developing Beta 0.9.1 | 2017-02-19 | Continue developing Beta 0.9.1 | -10
2017-02-26 | Finish Beta 0.9.1 and Official Release version 1.0 | 2017-02-26 | Finish Beta 0.9.1 and Official Release version 1.0 | 10
2017-02-27 | Making API guide | 2017-02-27 | Making API guide | -10
2017-03-03 | Finish API guide | 2017-03-03 | Finish API guide | 10
2017-03-04 | Deliver official version 1.0 | 2017-03-04 | Deliver official version 1.0 | -10
Formulas:
Date = IF([Date]<>"", [Date], "")